## Tasks
Tasks
Id | Task Title | Project | Parent Task | Status | Progress | Priority | Description | Assignee | To-do Items List | Planned End | Actual End | Created Date | Updated Date | Created By | Updated By
000040 | Milestone: submit draft report to supervisors |  |  | Completed | 100 | High |  |  |  | 5/10/2023 2:04:00 PM | 5/12/2023 2:05:00 PM | 2023-04-25 13:52 | 2023-05-12 16:54 | Ali Flows | Ali Flows
000039 | Conclusion: draft opportunities for future work or further development |  |  | Completed | 100 | High |  |  |  | 4/30/2023 2:25:00 PM | 5/12/2023 2:05:00 PM | 2023-04-25 13:52 | 2023-05-12 16:54 | Ali Flows | Ali Flows
000038 | Conclusion: draft a critical review of what you have achieved compared with your aims (or what you need to write here) |  |  | Completed | 100 | High |  |  |  | 4/30/2023 2:26:00 PM | 5/5/2023 2:12:00 PM | 2023-04-25 13:51 | 2023-05-12 16:54 | Ali Flows | Ali Flows
000037 | Critical review: draft a critical and realistic review of project management milestones, deliverables and time management. |  |  | Completed | 100 | Critical |  |  |  | 4/30/2023 2:26:00 PM | 5/5/2023 2:12:00 PM | 2023-04-25 13:51 | 2023-05-12 16:54 | Ali Flows | Ali Flows
000036 | Critical review: draft a critical and realistic review in terms of outcomes (or bullets for what you expect to cover) |  |  | Completed | 100 | Critical |  |  |  | 4/30/2023 2:26:00 PM | 5/5/2023 2:12:00 PM | 2023-04-25 13:51 | 2023-05-12 16:54 | Ali Flows | Ali Flows
000035 | Critical review: draft a critical and realistic review in terms of efficacy and performance (or bullets for what you expect to cover) |  |  | Completed | 100 | Critical |  |  |  | 4/30/2023 2:26:00 PM | 5/5/2023 2:12:00 PM | 2023-04-25 13:51 | 2023-05-12 16:54 | Ali Flows | Ali Flows
000034 | Critical review: draft a critical and realistic review of results (or bullets for what you expect to cover) |  |  | Completed | 100 | Critical |  |  |  | 4/30/2023 2:26:00 PM | 5/5/2023 2:12:00 PM | 2023-04-25 13:51 | 2023-05-12 16:54 | Ali Flows | Ali Flows
000033 | Implementation: Describe the evaluation approach (this is part of the Evaluation task, above) |  |  | Completed | 100 | High |  |  |  | 4/30/2023 2:26:00 PM | 5/5/2023 2:12:00 PM | 2023-04-25 13:51 | 2023-05-12 16:54 | Ali Flows | Ali Flows
000032 | Implementation: Describe the steps that a someone else will have to follow in order to use or generate output. |  |  | Completed | 100 | High |  |  |  | 4/30/2023 2:25:00 PM | 5/5/2023 2:11:00 PM | 2023-04-25 13:51 | 2023-05-12 16:53 | Ali Flows | Ali Flows
000031 | Implementation: Describe the steps that a someone else will have to follow in order to recreate your implementation. |  |  | Completed | 100 | High |  |  |  | 4/30/2023 2:14:00 PM | 5/5/2023 2:11:00 PM | 2023-04-25 13:51 | 2023-05-12 16:53 | Ali Flows | Ali Flows
000030 | Methodology / design: draft |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:14:00 PM | 5/5/2023 2:11:00 PM | 2023-04-25 13:50 | 2023-04-25 14:15 | Ali Flows | Ali Flows
000029 | Literature Review: draft Literature Review exploring background research, technology choices, existing apps etc |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:14:00 PM | 5/5/2023 2:11:00 PM | 2023-04-25 13:50 | 2023-04-25 14:15 | Ali Flows | Ali Flows
000028 | Project Management Considerations: draft Project Management Considerations |  |  | Completed | 100 | Medium |  |  |  | 4/30/2023 2:17:00 PM | 5/5/2023 2:11:00 PM | 2023-04-25 13:50 | 2023-05-12 16:53 | Ali Flows | Ali Flows
000027 | Introduction: draft report overview |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:22:00 PM | 5/5/2023 2:11:00 PM | 2023-04-25 13:50 | 2023-04-25 14:23 | Ali Flows | Ali Flows
000026 | Introduction: draft background |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:22:00 PM | 5/5/2023 2:10:00 PM | 2023-04-25 13:50 | 2023-04-25 14:24 | Ali Flows | Ali Flows
000025 | Introduction: draft Legal, social, ethical, and professional considerations |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:24:00 PM | 5/5/2023 2:10:00 PM | 2023-04-25 13:50 | 2023-04-25 14:24 | Ali Flows | Ali Flows
000024 | Introduction: draft Aims, Objectives and Scope |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:24:00 PM | 5/5/2023 2:10:00 PM | 2023-04-25 13:49 | 2023-04-25 14:24 | Ali Flows | Ali Flows
000023 | Introduction: draft Motivations |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:24:00 PM | 5/5/2023 2:10:00 PM | 2023-04-25 13:48 | 2023-04-25 14:24 | Ali Flows | Ali Flows
000022 | Milestone: Evaluation ready to run |  |  | Completed | 100 | Medium |  |  |  | 4/30/2023 2:24:00 PM | 5/5/2023 2:11:00 PM | 2023-04-25 13:46 | 2023-05-12 16:53 | Ali Flows | Ali Flows
000021 | Copy surveys and instructions into your report (or separate files for printing, if written in report) |  |  | Completed | 100 | Medium |  |  |  | 4/30/2023 2:24:00 PM | 5/5/2023 2:10:00 PM | 2023-04-25 13:46 | 2023-05-12 16:53 | Ali Flows | Ali Flows
000020 | Review and update your evaluation plan |  |  | Completed | 100 | Medium |  |  |  | 4/30/2023 2:24:00 PM | 5/5/2023 2:10:00 PM | 2023-04-25 13:46 | 2023-05-12 16:53 | Ali Flows | Ali Flows
000019 | Draft your excel spreadsheet for post-test survey results |  |  | Completed | 100 | Medium |  |  |  | 4/30/2023 2:24:00 PM | 5/5/2023 2:10:00 PM | 2023-04-25 13:45 | 2023-05-12 16:53 | Ali Flows | Ali Flows
000018 | Draft your post-test survey |  |  | Completed | 100 | Medium |  |  |  | 4/30/2023 2:24:00 PM | 5/5/2023 2:10:00 PM | 2023-04-25 13:45 | 2023-05-12 16:53 | Ali Flows | Ali Flows
000017 | Draft your evaluation plan in your report |  |  | Completed | 100 | Medium |  |  |  | 4/30/2023 2:24:00 PM | 5/5/2023 2:10:00 PM | 2023-04-25 13:45 | 2023-05-12 16:53 | Ali Flows | Ali Flows
000016 | Draft your test instructions for someone to follow |  |  | Completed | 100 | Medium |  |  |  | 4/30/2023 2:24:00 PM | 5/5/2023 2:10:00 PM | 2023-04-25 13:44 | 2023-05-12 16:53 | Ali Flows | Ali Flows
000015 | Draft your excel spreadsheet for pre-test survey results |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:25:00 PM | 5/5/2023 2:10:00 PM | 2023-04-25 13:44 | 2023-04-25 14:26 | Ali Flows | Ali Flows
000014 | Draft your pre-test survey |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:25:00 PM | 5/5/2023 2:09:00 PM | 2023-04-25 13:43 | 2023-04-25 14:25 | Ali Flows | Ali Flows
000012 | Milestone: Arte-fact completed ready for evaluation |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:25:00 PM | 5/5/2023 2:09:00 PM | 2023-04-25 13:43 | 2023-04-25 14:25 | Ali Flows | Ali Flows
000011 | Allow user to do multiple designs |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:24:00 PM | 5/5/2023 2:09:00 PM | 2023-04-25 13:43 | 2023-04-25 14:25 | Ali Flows | Ali Flows
000010 | Fix the API limit generation |  |  | Completed | 100 | Medium |  |  |  | 4/30/2023 2:13:00 PM | 5/5/2023 2:09:00 PM | 2023-04-25 13:42 | 2023-05-12 16:52 | Ali Flows | Ali Flows
000009 | Add more features |  |  | Completed | 100 | Medium |  |  |  | 4/30/2023 2:13:00 PM | 5/5/2023 2:09:00 PM | 2023-04-25 13:42 | 2023-05-12 16:52 | Ali Flows | Ali Flows
000008 | Design an icon |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:13:00 PM | 5/5/2023 2:09:00 PM | 2023-04-25 13:42 | 2023-04-25 14:25 | Ali Flows | Ali Flows
000007 | Edit UI, Add some options |  |  | Completed | 100 | Medium |  |  |  | 3/24/2023 2:13:00 PM | 5/5/2023 2:09:00 PM | 2023-04-25 13:42 | 2023-04-25 14:26 | Ali Flows | Ali Flows
000006 | Set up background |  |  | Completed | 100 | Medium |  |  |  | 4/30/2023 2:13:00 PM | 5/5/2023 2:08:00 PM | 2023-04-25 13:42 | 2023-05-12 16:56 | Ali Flows | Ali Flows